## To-Do List
2026
Generic Data Protection Project Plan
Task | Area | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
Personal Information Audit - Carry out an assessment of the personal data held by the council (both electronic and hard copy), where it comes from, who it is shared with, what it is used for, how you store it and how it is protected. Identify a ‘lawful basis’ for using the data, for example to deliver a contract with an individual. Does the council collect any sensitive personal data and why? Safeguarding, equal opportunities. | Audit | High | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 90% | Pending
Carry out a IT security assessment audit. Are cookies used on the website and if so why (do we actually need them)?, do computers have up to date software and fiewalls, encryption software for documents and emails, password protection (passwords are not shared or displayed publically, are home networks set to private (include staff and councillors) | Audit | High | Ongoing | 1st Aug 2018 | 31st Oct 2018 | 100% | Complete
Decide whether or not your council will need to carry out a Data Protection Impact Assessment. | Audit | Low | n/a | 1st Aug 2018 | 31st Oct 2018 | 100% | Complete
Ensure that the council has insurance liability cover which specifically covers prosecutions resulting from a data breach and put aside sufficient funds (up to 4% of income) should the council be fined for a data breach | Budget and Insurance | High | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 80% | Pending
Download LCPAS templates | Documentation | n/a | n/a | 1st Aug 2018 | 31st Oct 2018 | 100% | Complete
Review and update any contracts to meet the requirements of GDPR. | Documentation | High | Ongoing | 1st Aug 2018 | 31st Mat 2020 | 100% | Complete
Organise agreement required between PC's regarding Clerk sharing IT | Documentation | n/a | n/a | 1st Aug 2018 | 31st Oct 2018 | 100% | Complete
Ensure that minutes and agendas do not contain personal data | Housekeeping | High | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | Complete
Destroy documents, delete emails and electronic data containing personal data that is no longer needed in line with Retention Policy | Housekeeping | Medium | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 50% | Pending
Encrypt emails containing personal data. See also https://www.virtru.com/blog/encrypt-gmail/ | Housekeeping | High | Ongoing | 1st Aug 2018 | 31st Oct 2018 | 100% | Complete
Purchase cross shredder | Housekeeping | Medium | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Download PDF password protection software | Housekeeping | Medium | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Download PDF Mate Converter for adding passwords to PDF's | Housekeeping | Medium | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Register with ICO | ICO | High | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Appoint a Data Protection Officer | ICO | HIgh | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Agree on data back up process and ensure supplier if cloud based is in EU | IT | High | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Set up separate parish council email addresses for employees and councillors - possibly using .gov.uk | IT | High | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Add disclaimer to website contact page or create a box fill in with capture it | IT | HIgh | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Add disclaimer to Facebook | IT | n/a | n/a | 1st Aug 2018 | 31st Oct 2018 | 100% | n/a
Investigate MailChimp for mailing lists of less than 2000 | IT | n/a | n/a | 1st Aug 2018 | 31st Oct 2018 | 100% | n/a
Upgrade computers to windows 10pro and install Bitlocker that will encrypt the whole hard drive / AxCrypt | IT | High | Ongoing | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Change email disclaimer | IT | High | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Adopt Information Security Incident Policy | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 100% | Complete
Adopt Information Protection Policy | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 100% | Complete
Adopt or update Data Protection Policy | Policies | HIgh | Pending | 1st Aug 2018 | 31st Mar 2020 | 100% | Complete
Prepare Privacy Statements (or just one that covers everything) to give to individual’s whose data the council will hold (allotments, hirers, burials, job applicants etc) and upload to website | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Decide how we will gain consent and prepare Consent Forms. We will need to get parental consent for children under 17 | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Prepare a log for recording emails and phone calls from members of the public as evidence that consent to hold data has been obtained and start to use it. | Policies | HIgh | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Review or put procedures in place for dealing with a security breach. | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Review or put in place procedures for dealing with subject access requests - send all requests to DPO if we have one | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Vetting and Barring Policy required | Policies | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending
Review and adopt if required recording and filming of meetings | Policies | High | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Add GDPR Risk Assessment to Data audit | Risk Assessment | High | Complete | 1st Aug 2018 | 31st Oct 2018 | 100% | 1
Ensure that staff and councillors are aware of their individual responsibility for protecting data. To include: awareness of the risk of theft or loss of devices and the need to take sensible measures to protect them from loss or theft, protect data at home, not sharing, housekeeping of historic data at home. | Training | HIgh | Pending | 1st Aug 2018 | 31st Mar 2020 | 100% | Complete
Prepare GDPR Councillors checklist and getting them to sign up | Training | High | Pending | 1st Aug 2018 | 31st Mar 2020 | 0% | Pending